## Gantt Chart Template
To edit this Gantt chart template, you have to make a copy on your Drive: Go to File > Make a Copy. Manage your projects with the help of GanttPRO Gantt chart software
Buck Converter | Start date | End date | Assigned | Status | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07
Macro Model Simulations | 2026-10-26 | 2026-11-03 | All | In process
Optimize Switches + Passives | 2026-10-26 | 2026-10-30 | Oliver | In process
Testbench + Top Level Sim | 2026-10-30 | 2026-11-01 | Dylan | In process
Schematic Design | 2026-10-28 | 2026-11-03 | Dylan | In process
Analysis and Spec Planning | 2026-10-26 | 2026-11-03 | Hussain | Open
Subblock Design | 2026-11-01 | 2026-11-20 | All | Open
PWM Generation | 2026-11-01 | 2026-11-20 | Hussain | Open
Subtask Comparator | 2026-11-04 | 2026-11-10 | Dylan | Open
Subtask Wave Generation | 2026-11-08 | 2026-11-20 | Hussain | Open
Error Amplifier Design | 2026-11-01 | 2026-11-09 | Oliver | Open
Voltage Sensing Network | 2026-11-06 | 2026-11-10 | Dylan | Open
Gate Driver | 2026-11-04 | 2026-11-14 | Hussain | Open
Level Shifter | 2026-11-10 | 2026-11-15 | Oliver | Open
Other Blocks | 2026-11-15 | 2026-11-20 | Dylan | Open
Top Level Transistor Design | 2026-11-20 | 2026-12-09 | All
FOM Improvement Interations | 2026-11-20 | 2026-12-09 | All
Sub Block Optimization/Redesign | 2026-11-20 | 2026-11-30 | All
Circuit Debugging | 2026-11-20 | 2026-12-09 | All
Insert new rows ABOVE this one

## Assignees and Status
Assignees | Status
Dylan | Open
Hussain | In process
Oliver | Closed
All | Done
Alex